## Sheet1
User Story | Priority | Grouped | Points | Description | STATUS | Comments
After Placing an Order Staff Can Book In Stock | M | B2B | 12 |  | COMPLETED
Narta Exchanger should be able to read responses and update | M | B2B | 8 | Need to set up CRON Job to read PORs and INVs
Smart Claims When Booking In | C | B2B | 4 | Staff could be notified of price differences after they place an order and when they book in stock that the price they bought the product has changed
Renewed Inventory Item price should show up. | M | Stock | 1 | After making a claim/submitting a claim, it should show up In the product view for that item
Claims with more incremental pending/ completed status | C | Stock | 4 | When making a claim we can stagger the completion of a pending claim so that it is not marked as complete straight away and rather can be manually done so later.
Interest Free Markups | M | Admin | 4 | Interest Free Markups, need to create a right click context item for categories page. These are displayed when searching through products/ on product view page. | COMPLETED
Loading Value | C | Admin | 4 | Manager can set a loading value for the pricing breakdown so the prices are inflated to the Staff members
In Stock Items Overview in breakdown | S | POS | 6 | When seeing the net breakdown for an item, it would be good to see the items that are in stock and what price they were purchased. | COMPLETED
Store Specific Deals | C | Core | 32 | HO wants to be able to offer store specific deals to members.
Sort by Sold | S | Merch | 2
Core Ranges | C | Merch | 16
Barcode Scanner Integration | M | Stock | 16 |  | COMPLETED
Historic Pricing | M | Core | 4 |  | COMPLETED
I want to be able to see previous payments | M | Invoicing | 4 | Be Able to see previous payments under 'Adjust Store Credit Limit' | COMPLETED
I want to be able to deny stores from placing orders | S | Invoicing | 2
I want to be able to easily reverse an invoice | M | Invoicing | 2 | Created similar invoice with REV appended to invoice and same prices. | COMPLETED
Delete Invoice | M | Invoicing | 2 |  | COMPLETED
Historic Pricing | M | Core | 2 |  | COMPLETED
Flag Orders | S | Invoicing | 2 | When a certain order number is put into the invoice in IRP a popup will show up saying to check why it has been flagged, user can then do so by going to 'Reserved Orders' in IRP currently.
Date Input Warnings | C | Invoicing | 2 | When putting in dates, if the newly input month isn't within a 6 month radius then display a warning
Remove Old Stores | C | Invoicing | 2 | When putting in new invoices, old stores still come up which can be annoying
Duplicate Invoice Numbers Issue | S | Invoicing | 4 | When putting in an invoice, user needs to be warned if the invoice number has already been input beforehand
Be able to easily see stores invoices | C | IRP/ Backend | 4 | Be able to search through all store invoices, example used "Beenleigh closed down so we needed access to an invoice where a customer claims he paid for an item but he did not pick it up"
Be able to have a way to easily differentiate Internal Extended Credits | C | IRP/ Backend | 8 | Another due date for stores invoices for credit given in verbal agreement.
Open to buy needs to be affected by the extended credit given above. | M | IRP/ Backend | 8 | The extended credit
Dynamic Footer for Invoice for Layby items | C | POS | 4 | Layby T & C changes - can change by store etc.